## Sheet1
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
|  | 5.okt-11.okt | 12.okt-18.okt | 19.okt-25.okt | 26.okt-1.nov | 2.nov-8.nov | 9.nov-15.nov | 16.nov-22.nov | 23.nov-29.nov | 30.nov-6.des | 7.des-13.des
Task | Name
First meeting & Research | bar: Week 1 to Week 2
Meeting with client | Project manager (PM)
Content writing | coworker1
Taking and editing pictures | coworker2
SEO | coworker3 + PM
Design | bar: Week 2 to Week 4
Create identity elements | coworker1 + PM
Create layouts for pages | coworker2
Second meeting | Project manager
Development | bar: Week 5 to Week 8
Build website | cw 1-2-3 + PM
Testing | bar: Week 9 to Week 10
Initial testing | cw 1-2 + PM
Uploading site and second testing | cw 1-2 + PM